IMPLEMENTATION GUIDE

How to Deploy Your California Harassment Prevention Training

# COMPLETE TRAINING PACKAGE CONTENTS

You now have a complete, California-compliant harassment prevention training system ready for immediate deployment:

| Document | Purpose | When to Use |
| --- | --- | --- |
| Facilitator Guide | Complete script with timing, discussion prompts, and teaching notes for delivering training | Review before every training session |
| Content Package | Slide deck specs, video scripts, and 10 interactive scenarios for live discussion | Build slides & videos from these specs |
| Certificate Template | SB 513-compliant certificate with all required metadata fields | Generate after each training session |
| Attendance Roster | Sign-in sheet with participant acknowledgments and trainer certification | Print for each training session |

# 3-DAY RAPID DEPLOYMENT TIMELINE

Follow this timeline to go from contract to completed training in 72 hours:

## DAY 1: Preparation (4 hours)

- Morning: Client kickoff call

• Obtain final employee roster (names, job titles, supervisor status)

• Confirm training format (webinar vs. in-person)

• Schedule training date/time

- Afternoon: Customize materials

• Add company logo to slides

• Pre-fill certificates with company name

• Pre-populate attendance roster with employee names

• Send calendar invite to all participants

## DAY 2: Build Presentation (6 hours)

- Create PowerPoint slide deck using provided specifications

- Record or source videos (or plan to deliver content live without pre-recorded videos)

- Run through facilitator guide and practice timing

- Test webinar platform OR confirm in-person room setup

## DAY 3: Deliver Training

- Conduct live training (2 hours supervisor / 1 hour employee)

- Collect signed attendance roster

- Generate and distribute certificates within 24 hours

- Upload records to client's HR system (or provide copies for their files)

# PRICING & REVENUE MODEL

## Recommended Fee Structure

| Service Component | Cost | Notes |
| --- | --- | --- |
| Setup & Customization (one-time) | $500-750 | Loss leader - builds trust |
| Live Training Delivery (per session) | $1,500-2,500 | Primary revenue source |
| Certificate Generation & Records Management | $5-10/person | Covers admin time |
| Monthly HR Advisory Retainer | $500-2,000/mo | HIGH-VALUE TARGET |

Example: Button Nose Grooming (50 employees)

- Setup: $750

- Supervisor training (15 employees): $2,000

- Employee training (35 employees): $2,000

- Certificates & admin: $500

- TOTAL INITIAL REVENUE: $5,250

- Monthly retainer (converted): $1,200/month = $14,400/year

# KEY SUCCESS FACTORS

- Use training as loss-leader to build relationships

Training gets you in the door. Real revenue comes from ongoing monthly retainers for strategic HR support.

- Deliver exceptional live experience

Your MPA background and 10+ years experience = immediate credibility. Use interactive discussions to demonstrate depth of knowledge.

- Emphasize PAGA penalty avoidance ROI

$500/employee PAGA penalties × 50 employees = $25,000 exposure. Your $5,250 service is a 5:1 ROI.

- Automate certificate generation

Build simple mail merge or web form to generate certificates instantly from attendance roster. This reduces admin time and improves client experience.

- Upsell to retainer within 30 days

During or immediately after training, identify 2-3 compliance gaps. Offer 30-day complimentary consultation, then convert to monthly retainer.

🚀 YOU'RE READY TO LAUNCH

All materials are production-ready. Schedule Button Nose Grooming and start generating revenue this week.